## Sheet1
	Pattern Name			Patlet	Author	Date		1
Value Stream Pattern Language							Value Stream	2
	Spirit of the Game			Rules create loopholes. Therefore: Use the rules as a guide, but be driven by The Spirit Of the Game in cases where the rules' applicability is ambiguos or contentious.	Jens Østergaard & Lachlan Heasman	2012-05-08	Value Stream	3
	Sprint Planning			Sprint Planning is the transition along the value stream between the Product Backlog and the Development Team's work plan	Neil Harrison	2012-05-08	Value Stream	4
	Daily Clean Code			Every night when you go to bed, the code should at least build cleanly and ideally should be shippable.	Neil Harrison	5/1/2010	Value Stream	5
	Small Items			Big items are hard to estimate; Therefore: Break down items so they are small enough to estimate with confidence	James O. Coplien	2010-05-01	Value Stream	6
	Whack the Mole			A separate bug-tracking system leaves an increasing bug inventory; Therefore: Fix bugs when they arise, relegating bugs that will require a large amount of work to the Product Backlog. Maybe needs clarification against Daily Clean Code.	James O. Coplien	5/1/2010	Value Stream	7
	Estimation Points			You need up-to-date estimates, yet it's much work to re-estimate everything as the velocity improves. Therefore: use unitless relative estimation against a baseline	James O. Coplien	2010-05-01	Value Stream	8
		Accountable Estimates		The Product Backlog must be estimated by the people who commit to the estimates. Therefore: have the Team develop cost estimates and the Product Owners develop Business Value estimates.	James O. Coplien	12/22/2010	Value Stream	9
		Pigs Estimate		Estimates should be grounded in reality rather than wishful thinking; Therefore: Let those who are going to do the work do the estimation	Gertrud Bjørnvig	5/1/2010	Value Stream	10
		Yesterday's Weather		People tend to set increasingly high goals for themselves to the point of not being able to achieve them; Therefore: Use the previous Sprint's velocity as the best indicator of the next Sprint's velocity	Joe Bergin	5/1/2010	Value Stream	11
		Updated Velocity		You want the velocity to reflect the team's current abilities, yet it takes time to know whether process improvements actually worked; Therefore: Update the velocity only if a new level is sustained for the past three sprints.	James O. Coplien	5/1/2010	Value Stream	12
		Teams that Finish Early Accelerate Faster		If you fail too many Sprints it's discouraging: failure comes from taking too many points into the Sprint. Therefore: use Yesterday's Weather to get about the right number of points; use Scrumming the Scrum to lubricate the acceleration; and realize the acceleration by taking on more work if you do finish early.	Jeff Sutherland	7/10/2012	Value Stream	13
		Kaizen Pulse also belong here?						14
		Regular Product Increment		In a complex environment, it is difficult to assess progress and meet business goals. Therefore: Develop a regular product increment both to keep on track and to meet market needs	Lachlan Heasman	11/19/2011	Value Stream	15
	Information Radiator			Kaizen is the core of Scrum, and improvement depends on transparency and visibility. Therefore: Create artifacts and roles that keep information visible to all stakeholders, and create ceremonies where information is exchanged and disseminated.	Swarm		Value Stream	15
	Product Backlog			Everyone needs to agree to what should be delivered and when. Therefore: Create a visible Product Backlog of Product Backlog Items	James O. Coplien	2010-05-01	Value Stream	16
		Aggregate Velocity		Velocity is a property of a product backlog and not of a team; Therefore: have all Scrum teams for a single product backlog estimate together using a common baseline and range	James O. Coplien	6/16/2012	Value Stream	17
		Spike		Sometime you need (perhaps arbitrarily time-boxed) activities whereby the Development Team helps the Product Owner clarify requirements. / Dropped — doesn't make sense in Scrum.	Ville & team	5/1/2010	Value Stream	18
		Set-Based Design		Sometimes it's hard to know which of several alternatives to pursue, yet the difference is crucial. Therefore: Pre-build each of several options as an exercise to mitigate risk.	Evan Leonard	1/4/2017	Value Stream	19
		Change for Free		Some PBIs are so context-free that they can easily be exchanged for others; Therefore: Allow the customer to add a PBI if the remove one of equal cost, thereby achieving higher value for the customer	James O. Coplien	5/1/2010	Value Stream	19
		Enabling Specification		Unexplored requirements cause unpleasant surprises; Therefore: The product owner should deliver enabling specifications that show that important questions have been raised and adressed	James O. Coplien	5/1/2010	Value Stream	20
		Estimation Range		Estimation isn't just about accuracy, but also about precision; Therefore: Handle estimates as ranges. I think that Release Range is a better pattern — this one looks too much like amplified guesswork. It's also kind of a microamangement thing and something more related to an old-style Project Management approach where individual items mattered more than delivering the Sprint	James O. Coplien	5/1/2010	Value Stream	21
		Granularity Gradient		Small items are easy to estimate, but it's a lot of work to break down big items into small items; Therefore: Break down just the items that you depend on in the near future	James O. Coplien	5/1/2010	Value Stream	22
		Refined Product Backlog		Alias for Definition of Ready	Neil Harrison	1/6/2015	Value Stream	23
		High Value First		PBIs have different values and costs; Therefore: To manage value in a rapidly changing environment, deliver the highest value PBIs first	James O. Coplien	5/1/2010	Value Stream	24
		Money for Nothing		You don't want to spend time building product that costs more than its long-term value; Therefore: Stop working when you have worked down the backlog to this point	James O. Coplien	5/1/2010	Value Stream	25
		Product Backlog Items		You want to organize work to optimize ROI; Therefore: Create PBIs to describe concrete product increments that increase value for stakeholders	James O. Coplien	5/1/2010	Value Stream	26
		Project Management		Scrum handles one product at a time, but you may have several revenue streams; Therefore: Handle several projects on a single product backlog	James O. Coplien	5/1/2010	Value Stream	27
		RechunkedPBIs		It's tedious to have too many fine-granularity PBIs deep in the Product Backlog; Therefore: Re-factor them back together into larger items	Ville Mäkinen	2010-05-01	Value Stream	228
		ROI		You need to order the items in the backlog; Therefore: order them such that you achieve the highest long-term ROI if delivered in the order of the Product Backlog	James O. Coplien	2010-05-01	Value Stream	29
		Specialized Velocities		It's hard to do Aggregate Velocity if you have too many teams; Therefore: Specialize teams (not individuals) and let each one estimate and build PBIs matched to their specialization	James O. Coplien	2010-05-01	Value Stream	30
		Running Average Velocities		You want the velocity to reflect the team’s current abilities, but it takes time to know whether process improvements actually worked. Therefore, set a running average of the most recent Sprints to calculate the velocity of the next Sprint.	Neil Harrison	2012-05-06	Value Stream	31
		Vacation PBI		If you are going to take time off from "real work," track the time and value of the Team Member's absence as a PBI on the Product Backlog.	James O. Coplien	3/23/2013	Value Stream	32
		Fixed-Date PBI		Some PBIs aren't scheduled by the PO, but reflect external dependencies or personal events such as vacation, or scheduled courses, conferences or vacations.	James O. Coplien	3/23/2013	Value Stream	33
		Definition of Ready		If work items are not precisely understood, development effort (and time) tend to balloon, which in turn cause the Sprint to fail. Therefore, deefine criteria which items must meet before they can be put on the Sprint backlog.	Neil Harrison	1/6/2015	Value Stream	34
	Down Time			You need both to support the long-term vision and give the whole team a sense of buy-in. Therefore: Fund periodic time for the team to innovate. (Superceded by Team Sprint and Set-Based Design)	James O. Coplien	3/20/2011	Value Stream	35
	Greatest Value			You want to reward good behavior at each level, yet you want the greatest value. Therefore: Let the vision drive to the value with the greatest scope.	Jeff Sutherland	6/20/2011	Value Stream	36
	Regular Product Increment			A backlog needs a vision, a view of the future that the team will help create	Lachlan Heasman	4/16/2011	Value Stream	37
	Sprint Pulse			Alias for Regular Product Increment.	Ville Reijonen	2012-03-02	Team	38
	Team Pulse			Alias for Regular Product Increment.	Ville Reijonen	2012-03-02	Team	39
	Daily Clean Code			Little housekeeping items don't make it as big schedule items; therefore: take care of them daily by insisting on continuous clean code. Maybe needs some clarification against Whack the Mole: "aiming" to have a result isn't a pattern, but a KPI.	Neil Harrison	4/17/2012	Value Stream	40
	Respsonsive Deployment			Working in rhythm is good, but so is smoothing out flow, and reducing the inventory of items ready to ship to the market. Therefore: Release products to the market as they become Done and are approved by the Product Owner in the middle of the Sprint.	Jim Coplien		Value Stream	41
	Value Stream Fork			If a product gets too big, the Value Stream can't really work as intended (to provide feedback, team autonomy, and customer absorbtion of features).Therefore: when a product gets large, split it into multiple autonomous products that form an ecosystem.	Jim Coplien		Value Stream	41
	Release Plan			The product owner can use the Product Backlog, together with teams' velocities, to make a release plan [Look at whether this is related to a Product Roadmap as part of the Value Stream pattern language. Maybe make it a little more explicitly Mike Cohn-ish. Maybe it's close, but it needs attention, particularly with respect to its relationship to a Roadmap]	Veli-Pekka Eloranta	9/1/2017	Value Stream	44
		Product Roadmap		A Product Backlog is a path, at any given time, through a roadmap whose business alternative decisions have been bound. Roadmaps are still a good idea and their relationship to the Product Backlog is instructive.	James O. Coplien	2013-03-20	Value Stream	45
		Release Range		Do not estimate releases as an absolute date, but as a range	Veli-Pekka Eloranta	8/22/2011	Value Stream	46
		Release Staging Layers		Release every Sprint, but don't release all Sprints to the full market. Create layers of release robustness to manage risk	James O. Coplien	3/20/2013	Value Stream	47
	Sprint			Both the time thing and the space thing (very very close to the Sprint backlog)	James O. Coplien	2012-05-08	Value Stream	48
		Emergency Procedure		Sometimes unexpected work arises during the Sprint, and there are regular rhythms in how to address them; Therefore: Define levels of escalation that resolve emergencies in the least disruptive form of escalation possible	Jeff Sutherland	5/13/2012	Value Stream	49
		Stop the LIne		Really really stop the line	Jens Østergaard and Neil Harrison	3/28/2013	Value Stream	50
		Daily Scrum		Because we have emergent requirements and uncertainty, the Development Team replans dailly to raise the chances of meeting their forecast. [This lives here because it's a ceremony to refine the value stream — it's Sprint Planning]	Neil Harrison, Lachlan Heasman, Jim Coplien	2014-10-15	Value Stream	51
			Daily Ritual	People skip or are late to Daily Scrums; Therefore: make it attendance part of the culture by establishing a ritual of the same time and actions every day.	Neil Harrison	2013-03-09	Team	52
			Pigs Talk				Team	53
			Incremental Replan	Even at the beginning of a Sprint, there are so many unknowns that it is impossible to create a perfect plan; Therefore: each day use the Daily Scrum to incrementally replan (dup of Daily Scrum itself? — probably not quite.) (I recommend folding this into Daily Scrum. We should audit whether we've done that — joc)	Neil Harrison	2013-03-09	Team	54
			Round-Robin Status	It is easy to focus what you are working on, and neglect the rest of the team; Therefore: Each person in turn gives status.	Neil Harrison	2013-03-09	Team	55
			Daily Open Kimono	The Product Owner needs to know what is going on, but status summaries often omit important details; Therefore: the Product Owner attends the Daily Scrum (alias for Pigs Talk) (破)	Neil Harrison	2013-03-09	Team	56
			Silent Product Owner	The Product Owner may try to manage the team during the Daily Scrum; Therefore: the Product Owner does not speak at the Daily Scrum.	Neil Harrison	2013-03-09	Team	67
			ScrumMaster Incognito	Problem : Team member look at SM during Daily Scrum Solution : SM goes away from the inner circle and become a chicken. Replaces pattern formerly named, "ScrumMaster turns into a chicken."	Jens Østergaard and Dina Friis	2014-10-15	Team	68
			Beatles at the Daily Scrum	Daily Scrum is a must in any Scrum implementation. To create an extra interest for the meeting add a little bit of fun. This can be done for	Jens Østergaard	12/11/2011	Team	69
			Substitute in Daily Scrum	Individual developers are sometimes absent from the Daily Scrum but it is important that the team know the status of their ongoing work. Therefore: Have another team member report on behalf of the absentee.	Ville Reijonen	2012-03-02	Team	60
		Sprint Retrospective			Neil Harrison and Mike Beedle	2013-07-02	Sprint	61
	Sprint Backlog			The team needs a list to guide production work; Therefore: Make a Sprint Backlog that lists all work in a Sprint	Mike Beedle and Ademar Aguiar	11/11/2010	Value Stream	62
		Sprint Backlog Item		The above patterns talk about the ordering of the work plan, being free on an SBI level and chuncked at a PBI level. Within PBIs developers can create or delete tasks at will	Dina Friis & Jens Østergaard	2013-03-28	Value Stream	63
		Dependencies First		Dependencies suck. Therefore: Handle them in the first half of the Sprint and abort the Sprint if you can't.	James O. Coplien	2012-06-16	Value Stream	64
		Swarming: One-Piece Continuous Flow		Development Team has the final say over the ordering of Sprint backlog items. One-piece continuous flow should be split out of this.	Jeff Sutherland	2013-03-13	Value Stream	65
		Developer-Ordered Work Plan		People want direction, but task lists decrease self-organization; Therefore: Work from an unordered sprint backlog	James O. Coplien	2010-05-01	Value Stream	66
			First Things First	Pattern on working the top of the backlog (破)	Jeff Sutherland	2013-03-13	Value Stream	67
			Work the Top of the Backlog	Pattern on working the top of the backlog (破)	Jeff Sutherland	2013-03-13	Value Stream	68
		Burndown Chart		The obvious	Alan O'Callaghan	2015-01-05	Value Stream	69
		Track DONE		It's easy to misinterpret the burn-down chart overly optimistically with respect to business value; Therefore: Track business value progress separately and in additional to incremental task completion — REMOVED and factored into Sprint Burdown	James O. Coplien	2010-05-01	Value Stream	70
	Definition of Done			You cannot achieve quality if everyone has a different definition of quality. Therefore: the team defines criteria of all work to be completed on usual work items.	Ville Reijonen	9/18/2015	Value Stream	71
		Automated Code Checks		Definition of DONE does not mean "Ready to Ship" / Solution : Work on automating checks of the code	Jens Østergaard	5/1/2010	Misc	72
		Definition of Done as Workflow		Team members must adhere to "Done" but also have to get their work done. Therefore: Integrate "Done" with the process, so the process tends to create results that adhere to the definition.	Ville Reijonen	3/2/2012	Team	43
	Value Areas			Too many people on one product dilutes focus, yet it's good to grow the business. Therefore: split the product when it grows to a certain point.	Cesário Ramos	4/10/2016	Value Stream	71
	Sprint Review			The dialog between the business and development is set aside during actual production but production and the business need to be kept in sync; therefore, provide the Product Owner and other stakeholders the opportunity to create feedback about what the Development Team has produced	Neil Harrison	2013-05-03	Value Stream	73
	Sprint Goal			A Sprint, by itself, is simply a time box for development that only coincidentally actually delivers something useful. Running development on coincidences is not a recipe for success; Therefore: Create a short statement of the value that the team intends to create during the Sprint.	Neil Harrison and Jeff Sutherland	5/9/2012	Value Stream	74
	Vision			A backlog needs a vision, a view of the future that the team will help create	Lachlan Heasman	9/21/2011	Value Stream	75
	Visible Status			Create status reports that show daily status (within the sprint) and larger project status, and post them where all development team members can see them..	Neil Harrison	6/14/2012	Value Stream	76
	Fixed Work			Some work must be done on the team, but is difficult to estimate a closed work item. Therefore: Compartmentalize both recurring work and occasional spikes of work, particularly those that support the Product Owner process instead of directly building potentially shippable product	James O. Coplien	2010-05-13	Value Stream	77
		Domino Effect		One task can become "un-completed" if later work surfaces an emergent requirement; Therefore: Adjust all burn-down charts appropriately. [Can't remember why this pattern was interesting or special, and until we can remember that, we throw this out.]	James O. Coplien	2010-05-01	Value Stream	78
		Product Backlog Refinement Meeting		Replaced by "Refined Product Backlog"	James O. Coplien	3/20/2011	Value Stream	79
	Product Wake			All good things must come to an end	James O. Coplien	2016-07-01	Value Stream	79
	Work Flows Inward			Value Stream	Jim Coplien and Neil Harrison	2004-06-06	Value Stream	80
Process Improvement							Process Improvement	81
	Sauna Sprint Review			People need motivation; therefore, celebrate success with an extended sauna and champagne / Folded into Sprint Review.	Jukka Järvelä	2010-05-11	Process Improvement	82
	Fair Memory			People tend to focus on recent events, but the whole sprint is important. Therefore: Keep a log of sprint events	Dina Friis	2010-05-01	Process Improvement	83
	Sprint Retrospective				Neil Harrison and Mike Beedle	2013-07-02	Sprint	84
	Scrumming the Scrum			Process improvement is a primary goal of Scrum; Therefore: Use Scrum itself to manage and give visibility to Kaizen initiatives	Jeff Sutherland	2011-05-05	Process Improvement	85
	Impediment List				Gabrielle Benefield	2011-05-01	Process Improvement	86
	Historical Retrospective			Projects too often re-invent the wheel; Therefore: Start each new project with a retrospective over similar historic projects	James O. Coplien	5/14/2011	Process Improvement	87
	Learning Register			Aggregate retrospective results into a collection of foundational, long-term learnings (from PRINCE2)	James O. Coplien	5/23/2011	Process Improvement	88
	One Step at a Time			If you change multiple things at once, it's hard to know which one led to an improvement. Therefore: make one process improvement at a time	Neil B. Harrison	6/29/2012	Process Improvement	89
	Happiness Metric			Retrospectives are not effective; Therefore: focus on the improvement that will increase the team's happiness the most.	Neil B. Harrison and Jeff Sutherland	3/8/2013	Process Improvement	90
	Testable Improvements			You don't know if your improvement efforts are effective; Therefore: create self-improvement actions that can be measured whether they are being done or not.	Neil B. Harrison	3/8/2013	Process Improvement	91
	Create Knowledge			As the number of teams using Scrum grows they will face impediments and create valuable knowledge on solving them in their specific setting. Therefore: Form optimization teams consisting of people from the various Scrum Teams to capture the created knowledge so that the teams and organization can learn from it. / Deprecated per mail from Cesário 23 March 2017 21:58.	Cesário Ramos	2013-05-25	Process Improvement	92
							Process Improvement	93
Product Organization Pattern Language							Product Organization	94
	Community of Trust			Where it all begins. Link to Spirit of the Game	Jim Coplien and Neil Harrison	2004-06-06	Product Organization	95
	Conway's Law			Self-organisation is good but any group of human beings needs some basic, static organisation that reflects knowledge, change, and expediency. Therefore: Create an organisation whose primary structure localises the primary arenas of decision-making.	Jim Coplien	2014-10-22	Product Organization	95
	Birds of a Feather			Product development is one dimension of organizational structure; core competencies are another, but have no home in the basic Scrum structure, Therefore: create cross-cutting structures for competency growth.	Jim Coplien	2017-01-04	Product Organization	95
	Product Pride				Gabrielle Benefield et al.		Product Organization	96
	Radio Product Owner			meeting (telling on funny joke, play a song, etc), during the meeting (eating cake, drawing emotions), after the meeting (again a funny joke, etc.) Being folded in to Information Radiator.	Lachlan Heasman	2010-05-01	Product Organization	97
	Scrum of Scrums			When more then one Development Team needs to work together to create a potentially releasable product Increment, inter-team coordination warrants explicit attention.	Cesario Ramos	2016-04-08	Product Organization	98
	Organizational Sprint Pulse			An organization's organs can get out of step. Therefore: Synchronize sprints with the same dates at least once a month.	Dina Friis, Gertrud Bjørnvig	2010-05-01	Product Organization	99
	New Team Bootstrap			Teams need help getting off the ground. Therefore: align each new team with an experienced Scrum coach to help them succeed.	Ville Reijonen	2012-03-02	Team	100
	Team By the Side			The first team would have been well trained and well funded, the second and later teams would usually not get the same level of support. Therefore: Place a new team by the side of the existing Scrum team. [This seems to take the collective reflection of kaizen away from the startup team, and seems like it could lead to a cargo-cult team mimicking the first team. Let's revisit this one later.]	Kiro Harada	2012-03-02	Team	101
	Scrum Adapter			Isolated Scrum teams have an uphill battle in front of them. Therefore: Leaders of the groups adopting Scrum should join together to create an organizational entity that wraps the Scrum Teams with an interface to the rest of the organization. Instead of being a pattern in its own right this might fit into a chapter on the patterns process.	Evan Leonard	2015-01-19	Team	102
	Surrogate Product Owner			If the product being developed does not have a Product Owner, then the responsibility rolls all the way back to the team. / Dropped.	Jens Østergaard	2010-05-01	Product Organization	103
	Product Owner			You need a single, ordered product backlog. Therefore: Get a Product Owner with deep business experience and domain knowledge to create the backlog.	Jeff Sutherland	2010-05-17	Product Organization	104
	Single Mediator			If the team talks directly with customers, then it is hard to keep focus on priorities, but if there are too many connections between the team and the customer, there is too much noise. Therefore: The customer, Product Owner, and team form 1 - 2 - 3 chain links.	Veli-Pekka Eloranta	2010-11-11	Product Organization	105
	Product Owner Team			Sometimes a single Product Owner can't handle all the work to manage the Product Backlog. Therefore: Have a Product Owner Team.	Jeff Sutherland	2010-05-29	Product Organization	106
	Development Partnership			If a development effort is split across enterprises, break down the traditional boundaries between sides.	Jim Coplien	2016-04-16	Product Organization	106
	Chief Product Owner			If you have a Product Owner Team, responsibility can become diffuse. Therefore: Have a single Chief Product Owne who is responsible for the work of the Product Owner Team. / Folded into Product Owner Team.	Jeff Sutherland	2010-05-17	Product Organization	107
	Illegitimus Non Interruptus			There are always emergent requirements, and Scrum accommodates these in its velocity, yet some need business attention. Therefore: give the Product Owner discretion over some fraction of the team's velocity to accommodate market changes.	Jeff Sutherland	2011-05-05	Team	108
	Question Hour				Veli-Pekka Eloranta	2011-05-05	Team	109
	Rotating Guru				Monica Yap	2010-05-01	Distributed Scrum	110
	The Mist			Organizations do not spring spontaneously from the Earth: they self-organize around a vision, or around a person (such as a Product Owner) with a vision. While it would be nice if all organizations were born as Scrum organizations, most innovative organizations spring forth from tabla rasa or or born into a culture foreign to Scrum.	Jim Coplien	2016-07-01	Product Organization	111
	Out of the Mist			People learn to organise around shared visions. No longer needed because Vision now dovetails the resulting Context.	Jim Coplien	2016-07-01	Product Organization	111
	Development Team			The pigs.	Jim Coplien	2012-05-11	Product Organization	111
		Cross-Functional Team		It's costly to coordinate work across specialized organizations; Therefore: Colocate the specialties within a team so it has all necessary talent to deliver outcomes.	Dina Friis, Gertrud Bjørnvig, Jim Coplien	2012-02-23	Product Organization	112
		Stable Teams		You need predictability; Therefore: Keep teams stable over time	Gertrud Bjørnvig, Lachlan Heasman	2010-05-01	Team	113
		Remove the Shade		We value heroes but can also become overly dependent on them; Therefore: Displace the hero figure from the team to give the rest of the team room to grow	Dina Friis, Gertrud Bjørnvig	2012-10-28	Team	114
		Autonomous Team		Teams need to be able to work without outside interference (Self-Managing Team)	Neil B. Harrison	2013-03-25	Team	115
		Self-Organizing Team		You need to be autonomous before you self-organize.	Neil B. Harrison	2013-03-25	Team	116
		Developer-Ordered Work Plan		The team should have the final say over the ordering of sprint backlog items	James Coplien	2011-04-04	Team	117
		Collocated Team		How do you maximise communication in a team and support the seemingly random nature of it? Locate the entire team within talking distance	Lachlan Heasman	2013-05-16	Team	118
		Small Team		A large group of people working together will usually splinter into subgroups decreasing the overall group effectiveness. Therefore: Use small teams of people working closely together.	Lachlan Heasman	2013-05-16	Team	119
		Daily Scrum		Because we have emergent requirements and uncertainty, the Development Team replans dailly to raise the chances of meeting their forecast. [Link only — this is now in the Value Stream pattern language because of its role in re-building the Work Plan every day.]	Neil Harrison, Lachlan Heasman, Jim Coplien	2013-05-16	Team	120
		Team Sprint		The Product Owner is sometimes too externally focused; Therefore: let team members occasionally take control of the PBIs that they want to do	Veli-Pekka Eloranta	2011-08-22	Team	121
		Swarming: One-Piece Continuous Flow		Handoffs lead to poor feedback loops; Therefore: Have the team all work together on one item at a time	Jeff Sutherland	2013-05-21	Team	122
		Oyatsu Jinja		The company cafeteria is often on a different floor and disrupts the team efforts. Therefore: Create a Oyatsu Jinja ("snacks shrine").	Kiro Harada	2012-03-02	Team	123
		Snack Shrine		Alias for Oyatsu Jinja	Kiro Harada	2012-03-02	Team	124
		Kaizen Pulse		Continuous improvement is never continuous: therefore, go between plateaus	James O. Coplien	2013-03-27	Team	125
		Follow the Moon		Scrum cycles should be attendant to natural rhythms (破)	Gertrud Bjørnvig	2013-03-18	Team	126
		Beyond the Happy Bubble		Teams become victims of groupthink; Therefore: Have a catalyst who actively keeps the team a bit uncomfortable	Gabrielle Benefield	5/1/2011	Misc	127
		Scrumming the Scrum		Use Scrum and its Product Backlog to keep improving every Sprint	Jeff Sutherland	2013-03-08	Team	128
		Producer Roles		There are way too many roles, yet all the roles seem important. It looks like there is no way to reduce the bureaucracy. Identify each role as a producer, supporter, or roles that add no value to the project (deadbeats), and eliminate the deadbeats	Jim Coplien and Neil Harrison	2004-06-06	Team	129
		Norms of Conduct		A team is unable to discuss issue; things are unsaid, questions are unanswered, and solutions are not explored; Therefore: create norms of conduct to promote constructive conflict and discussions.	Cesario Ramos	2013-03-08	Team	130
		Circle Of Trust		Depending on others for your success fosters micromanagement; Therefore: develop a virtuous cycle of trust and accomplishment	Neil Harrison	2013-03-08	Team	131
		Distribute Work Evenly		Counterbalance to Domain Expertise in Roles, to make sure there's no starvation or blocking	James Coplien	2014-07-15	Team	131
	Domain Expertise in Roles			People like to focus and excel: Therefore, encourage specialization at the framework level and don't discourage it at the development team level	James Coplien	2014-07-15	Team	131
	Small Red Phone			Critical personnel should never be out-of-reach; Therefore: Give each one a cell phone as an ever-ready hotline to be used in emergencies	James Coplien	2011-04-30	Team	132
	ScrumMaster			Even self-organizing teams need leadership. Therefore: hire a ScrumMaster to challenge and lead the Team	Neil Harrison	2012-04-18	Team	133
		Coach		Teams may know their level of performance but not now how to improve; therefore: have a ScrumMaster to help chart a path to improvement	Neil Harrison	2012-04-18	Team	134
		Product Owner Trainer		New Product Owners often lack the context and skills for doing their job in a Scrum way; therefore: Have the ScrumMaster support the Product Owner through advice and education	Neil Harrison	2012-04-18	Team	135
		Firewall		There are always those who want to "help," though such "help" is a distraction; therefore: the ScrumMaster insulates the team from unwanted distractions	Neil Harrison	2012-04-18	Team	136
		Catalyst		Scrum depends on collaboration for success; therefore: Create an environment in which team members WANT to come together to communicate and collaborate, as well as provide opportunities for them to come together.	Neil Harrison — removed	2012-04-18	Team	137
		Cheerleader			Neil Harrison	2012-04-18	Team	138
		Knight of the Mirrors			Neil Harrison	2012-04-18	Team	139
		DoneMaster			Neil Harrison	2012-04-18	Team	140
		Sheepdog			Neil Harrison	2012-04-18	Team	141
		Scrum (Master) Coach			Lachlan Heasman	2014-10-17	Team	142
		Change Agent		Referenced in ScrumMaster pattern. I don't think it's a separately introducible pattern and I think it's already covered by ScrumMaster and by Catalyst. We should decide whether to keep it and, if not, remove the references to it.	Neil Harrison	2015-04-22	Team	142.5
	Scrumming the Scrum			Process improvement is a primary goal of Scrum; Therefore: Use Scrum itself to manage and give visibility to Kaizen initiatives	Jeff Sutherland	2011-05-05	Process Improvement	143
	Boot Camp			Multi-site teams have difficulty interfacing person-to-person; Therefore: bond organizational members by working together in an intensive Boot Camp	Monica Yap	2010-05-01	Distributed Scrum	144
	Meta Scrum			Run the enteprise as a Scrum	Sutherland & Evan	2016-05-26	Product Organization	145
	Quantum Entanglement			A pattern for distributed teams. Kickoff together, stabilise then move apart. Bring back together at key points and if velocity drops to stabilize. / Dropped.	Gabrielle Benefield	2010-05-17	Distributed Scrum	145
	Developing in Pairs			Two sombreros are better than one	Jim Coplien and Neil Harrison	2004-06-06	Team	146
	The Water Cooler			Provide a place for interaction. Link to Snack Shrine!	Jim Coplien and Neil Harrison	2004-06-06	Team	147
	Self-Selecting Team			How teams form. Alternative to Stable Teams.	Jim Coplien and Neil Harrison	2004-06-06	Team	148
	Thought Leader			Direct management intervention stimies self-organization; Therefore: let managers convince a leader on the team, who takes the issue to the team. (Creatively subverts the ability of a team to manage itself?)	Gabrielle Benefield	2010-05-16	Team	149
	Return and Report			Open-ended assignments create uncertainty and stress, and undermine trust; Therefore: establish a future point at which status will be reported. [Removed]	Neil Harrison	2013-03-08	Team	150
	Improvement Community			You have a vision for change about how other teams do their work, to better cooperate with your own team or to improve overall system performance, but its not clear how to go about it. Therefore: Two or more Teams agree to work through system level problems together; each Team elects a member to represent them in an Improvement Community and consents to follow the agreements made by the community. / Folded into Birds of a Feather.	Evan Leonard	2013-05-16	Team	151
	Impediment Removal Team			Large impediments require large effort to remove. Who should do this work? Therefore, create a Scrum team whose work it is to remove impediments. Instead of being a pattern in itself, fit into Scrum of Scrums.	Evan Leonard	2015-02-19	Team	152
	Norms of Conduct			A team is unable to discuss issue; things are unsaid, questions are unanswered, and solutions are not explored; Therefore: create norms of conduct to promote constructive conflict and discussions.	Cesario Ramos	2013-03-08	Team	153
	Follow the Leader			When it comes to Scrum issues, the Development Team should follow the ScrumMaster — Dropped	Jens Østergaard	2013-03-08	Team	154
								155
Scaling Scrum Pattern Language - FIXME: Make sure all of these have a new home!							Scaling Scrum	156
	Scrum of Scrums			When more then one Development Team needs to work together to create a potentially releasable product Increment, inter-team coordination warrants explicit attention.	Cesário Ramos	2016-04-08	Scaling Scrum	157
	Aggregate Velocity			Velocity is a property of a product backlog and not of a team; Therefore: have all Scrum teams for a single product backlog estimate together using a common baseline and range	James O. Coplien	2010-05-01	Scaling Scrum	158
	Specialized Velocities			It's hard to do Aggregate Velocity if you have too many teams; Therefore: Specialize teams (not individuals) and let each one estimate and build PBIs matched to their specialization	James O. Coplien	2010-05-01	Scaling Scrum	159
	Project Ready Criteria			Unclear requirements are a common problem. Therefore: have "Ready" criteria that must be met before development starts.	Dan Greening	2012-03-03	Product Organization	160
	Portfolio Management				Dan Greening	2012-03-03	Scaling Scrum	161
		Limited Duration Projects		You can't release every Sprint, so limit the amount of time for a project.	Dan Greening	2012-03-03	Scaling Scrum	162
		Portfolio Backlog		20% of the work generates 80% of the revenue. Therefore: focus on the big winners at the portfolio level, and create a priority list of projects.	Dan Greening	2012-03-03	Scaling Scrum	163
		Portfolio Standup		Large enterprises manage many projects, but the market and the world for those projects changes. Therefore: have weekly standups to refine the portfolio backlog.	Dan Greening	2012-03-03	Scaling Scrum	164
		Project Ready Criteria		Unclear requirements are a common problem. Therefore: have "Ready" criteria that must be met before development starts.	Dan Greening	2012-03-03	Product Organization	165
		Project Management		Scrum handles one product at a time, but you may have several revenue streams; Therefore: Handle several projects on a single product backlog	James O. Coplien	2010-05-01	Scaling Scrum	166
							Scaling Scrum	167
Scrum Core Pattern Language							Scrum Core	168
	Daily Scrum				Neil Harrison, Lachlan Heasman, Jim Coplien	2010-11-11	Scrum Core	169
	Release Burndown			No longer part of Scrum?	Mike Beedle	2010-11-11	Scrum Core	170
	Release Planning Meeting			No longer part of Scrum?	Mike Beedle	2010-11-11	Scrum Core	171
	ScrumMaster				Neil Harrison	2012-04-18	Scrum Core	172
	DoneMaster				Neil Harrison	2012-04-17	Scrum Core	173
	Catalyst				Neil Harrison	2012-04-17	Scrum Core	174
	Scrum Team				Mike Beedle	2010-11-11	Scrum Core	175
	Pulse			Uncertainty about the duration of a work episode prevents the work from being done effectively, so work in time units of uniform length	Neil Harrison	2013-05-04	Scrum Core	176
	Sprint			The Value Stream needs expression as series of release units over time; therefore, divide up the release stream both timewise and product-increment-wise into fixed-length time units called Sprints	Jim Coplien	2010-11-11	Scrum Core	177
		Uniform Window			Neil Harrison	2013-03-09	Scrum Core	178
	Sacred Schedule			If you don't end on time, you don't know where you are; Therefore: Don't put off sprint termination, even for a day.	Joe Bergin	5/1/2010	Scrum Core	179
	Sprint Backlog				Mike Beedle	2010-11-11	Scrum Core	180
	Sprint Burndown				Alan O'Callaghan	2010-11-11	Scrum Core	181
	Sprint Planning Meeting			There is a discontinuity between "what" and "how" in the Value Stream; therefore: create a ceremony to manage that transition	Mike Beedle and Ademar Aguiar	2010-11-11	Scrum Core	182
	Sprint Retrospective			You need a focal point for process improvement, because true continuous improvement is inefficient. Therefore: Convene a periodic ceremony to focus on process improvement	Neil Harrison and Mike Beedle	2013-07-02	Sprint	183
	Scrum Board			What is this?	Alan O'Callaghan	2014-01-05	Scrum Core	184
	Product Owner			You need a single, ordered product backlog. Therefore: Get a Product Owner with deep business experience and domain knowledge to create the backlog.	Jeff Sutherland	2010-05-17	Value Stream	185
	Product Backlog			Early in the value stream, you need to share the vision and create a foundation to start delivering. Therefore: Create a visible ordered list that articulates an ordered delivery of Product Increments that realize the Product Owner's vision	James O. Coplien	2010-05-01	Value Stream	186
	Change Management				Evan Leonard		Misc	187
		Electric Field						188
		Are We There Yet?		It's hard to know if you're doing what you say you're doing. Therefore, create a “scorecard” for Scrum Teams to periodically fill out that checks to see how Teams are using the agreed on Roles and Policies.	Evan Leonard	2/15/2012	Misc	189
		No More Rationalizations		Teams rationalize their impediments, which can impede progress. Therefore: Have each team work rationalized impediments with the Product Owner.	Evan Leonard	2/15/2012	Misc	190
		Consilience Team		You need a single point of focus to take things forward; therefore: Create a Scrum Team	Evan Leonard	2/15/2012	Misc	191
		Working Agreements		The Team often has a hard time making its work visible; therefore: Make it visible, as on a Wiki. (This is old and superceded by Norms of Conduct)	Evan Leonard	2/15/2012	Misc	192
		Coherent Theory		Analysis paralysis can kill you; therefore: Keep going only until the value of additional theory-building outweighs the value of taking it forward	Evan Leonard	2/15/2012	Misc	193
		Enduring Change		Teams left to themselves fall away from Scrum. Therefore: by putting upper and middle management support in place and empowering the teams to define impediments, the organization becomes self-sustaining.	Evan Leonard	2/15/2012	Misc	194
		Prepared Environment		While executive management may push Scrum, they're too far removed from the troops to support them. Therefore: form a middle management team whose job it is explicitly to support the Scrum transition at the grassroots level.	Evan Leonard	2/15/2012	Misc	195
		Fire Keeper		Teams need to surface and deal with tacit fear, but raising fear can breed fear. Therefore: create a role, like the ScrumMaster, to hold team fears and hold them in an objective light.	Evan Leonard	2/15/2012	Misc	196
		Bumper Bowling		It's tempting to do Scrum in a way that doesn't work. Therefore: have a deeply experienced ScrumMaster encourage a bounded direction for team evolution and growth.	Evan Leonard	2/15/2012	Misc	197
		North Star		It's easy to get lost in details and local optimizations during development-level Kaizen. Therefore: have the Product Owner establish the vision of the big picture to rally the team to a concerted direction.	Evan Leonard	2/15/2012	Misc	198
		Tension Backlog		Discussions about problems and direction can go on forever. Therefore: create an Impediment List to structure the team's discussion.	Evan Leonard	2/15/2012	Misc	199
		Documentation, by the people for the people		Documentation is difficult to make useful to those who need it, and difficult to get from those who write it. Therefore: let those who need the documentation write it.	Gabrielle Benefield, Neil Harrison	3/2/2012	Misc	200
Unlinked Patterns							Misc	201
	Crossing the Busy Street			Problem: It easy for a person or a team to fall into a state of mind where everything is good enough. This leads to a lack of interest in improving. Solution: Make inspection part of the process.	Dina Friis, Jens Ostergaard	3/31/2012	Misc	202
	Dream Team			Problem: People step outside the boundaries of there role, or do not fulfill the role. Solution: Create a job description that specifies the expected work and attitude.	Dina Friis, Jens Ostergaard	3/31/2012	Misc	203
	Couch Coach			Problem: Scrum Master lets the organization overrule Scrum guidelines. Solution: Make sure the Scrum Master fulfills her, or his, role.	Dina Friis, Jens Ostergaard	3/31/2012	Misc	204
	Sacred Schedule			If you don't end on time, you don't know where you are; Therefore: Don't put off sprint termination, even for a day. (Duplicate)	Joe Bergin	5/1/2010	Misc	205
	Bake-off			You have to face emergent requirements, but it's costly to terminate a whole line of inquiry before starting another; Therefore: Do set-based design, exploring several alternatives in parallel / Renamed from Bake-Off to Set-Based Design (separate entry above)	Evan Leonard	8/1/2016	Misc	206
	Checklists			You can't remember everything, and details are sometimes important; Therefore: Use checklists for frequent, repetitive tasks.	James O. Coplien	5/1/2010	Misc	207
	Overcommitment			Something happened in the sprint and the team is not going to make the sprint goal; Therefore: Execute emergency procedure / (Replaced by Emergency Procedure)	Jens Østergaard	5/1/2010	Misc	208
	Groupthink [DRAFT]			Problem: Team is not interested in retrospective / Solution : Find out if team is in groupthink. (Replaced by Pop the Happy Bubble)	Jens Østergaard	5/1/2010	Misc	209
	Patron-Supported Understanding			Problem: Scrum does not have buy-in from management / Solution : Educate, get a patron and show result	Jens Østergaard	5/1/2010	Misc	210
	Expose Sneak Paths			People outside team add work to the team / Solution : Make it transparent	Jens Østergaard	5/1/2010	Misc	211
	Expose Resource Leaks			Problem: People outside team steal resources / Solution : Make it transparent	Jens Østergaard	5/1/2010	Misc	212
	Can't Serve Two Masters			Problem: Team look at ScrumMaster (who is also team member) as an authority / Solution : Person drops one of the role	Jens Østergaard	5/1/2010	Misc	213
	External Feature Owner			Problem : Team is dependent an an external resource in the sprint and is unsure of how it is going / Solution : Make a team member responsible for the external resource, being proactive	Jens Østergaard	5/1/2010	Misc	214
	ScrumMaster Gets Fired			ProductOwner tells team that these PBIs have priority one, and the rest is priority two; Not only does the Product Backlog have to prioritized, PBIs also have to be sequenced. / Dropped 4/2/2017.	Jens Østergaard	5/1/2010	Misc	215
	Promising All The Gold in the World				Jens Østergaard	5/17/2010	Misc	216
	Continuous Integration			Scrum depends on early and frequent feedback, particularly about product quality; Therefore: Check in code when an increment is done, and immediately build the system against the changes.	Jeff Sutherland	5/18/2010	Misc	217
	Bad News First				Gabrielle Benefield	5/1/2011	Misc.	218
	Break Eye Contact			The ScrumMaster is drawn into the Daily Scrum too much; Therefore: The ScrumMaster should break eye contact to telegraph that Team members should be talking with each other	Gabrielle Benefield	4/26/2011	Misc.	219
	Build Less			The problem is to get to launch quickly. Therefore: Focus on what is important, and build less.	Gabrielle Benefield	5/1/2011	Misc.	220
	Constant Crisis				Gabrielle Benefield	4/26/2011	Misc.	221
	Four Minute Mile			The team has become complacent and may not be improving at all; Therefore: Give the team a Herculean challenge that helps them question their assumptions	Gabrielle Benefield	5/2/2011	Misc.	222
	Hackathon			Problem: Organisations become fixated on building to the business model and not allowing enough time for freedom of creativity. Solution: 24 hour hackathons quarterly, both internal to the organisation and external.	Gabrielle Benefield	5/1/2011	Misc.	223
	Hack Sprint			Problem: Teams can burn out and don't have time to step back and be creative or work on something they feel is important. Solution: Hack Sprints. One sprint every quarter for the Scrum team to create their own PB. This finally made it in as "Team Sprint."	Gabrielle Benefield	5/1/2011	Misc	224
	Involve The Managers			If people feel a need to help, give them something harmless to do	Gabrielle Benefield & Neil Harrison	5/1/2011	Misc.	225
	Helpers in Pairs			Instead offering part-time assignment of a team member, offer full-time assignment of two team members who understand Scrum well.	Kiro Harada	2012-03-02	Team	226
	Prove It Don't Plead It				Gabrielle Benefield	5/1/2011	Misc.	227
	Risk Backlog				Gabrielle Benefield	4/26/2011	Misc.	228
	Shark's Fin			Inexpert changes introduce bugs; Therefore: Introduce bugs to placate those who feel they need to contribute improvements.	Gabrielle Benefield	5/1/2011	Misc.	229
	Systemic Over Symptomatic				Gabrielle Benefield	5/1/2011	Misc.	230
	Definition of Done Baseline			It's common to set the bar too high or too low for the definition of Done. Therefore: Set the definition of "Done" according to how most team members do their work. Dropped, because it sets the bar low at status quo, rather than challenging the team to consider value and a minimal standard that comes from the business instead of current engineering practice.	Ville Reijonen	3/2/2012	Value Stream	231
	System Level Definition of Done			You want uniform quality across teams with regard to certain quality criteria. Therefore: define a system-wide definition of Done that applies to all teams. - Dropped	Ville Reijonen	3/2/2012	Value Stream	232
	360° Feedback				Cesário Ramos	3/10/2013	Misc.	233
	All			Pictures	Esther Vervloed	11/15/2016	Misc.	234