## Sheet1
			Burndown Charts

Pattern or other work item	Brief Description	Developer's Estimated Delivery Date	Remarks

New administrative environment	People don't like Google Docs, &c. for administering the patterns, and Ademar has proposed a simpler alternative hosted on git or some other site. This can start as a prototype and then grow. / Further, Google Sites is going away.	Should be before ScrumPLoP 2015, to make sense and to be worth doing? Maybe shoot for Scrum PLoP 2017. / Currently no estimated delivery date — high risk.	Ademar is working on a DocuWiki solution. Builds on scrumbook.org work. / Timeline in mail from gsuite-noreply@google.com 3 Nov 2016 05:47UCT+1. Current drop-dead date is 2018/03/09.	aa
Sprint Planning	Copy editing and getting to Done	04/11/2017	Cope says Done. Mark says Done. And Cesário.	lh
Consistent citation format		02/11/2017	Cope is captain. Decided on Turabian / Chicago format.	cope
Superflous citations in Aggregate Velocity / Speciallized Velocities, and in Testable Improvements and Value Areas	The reference lists for these patterns contain references that are nowhere called out in the text.	10/11/2017		cr
Pop the Happy Bubble	Copy editing and getting to Done	14/11/2017	Done by Cope. And Lachlan. And Cesário. And Mark.	lh
Visible Status needs to convey urgency	Also copy editing and getting to Done	05/11/2017	Based on a lunch discussion with Kiro-san. Done according to Cope. And Mark. And Lachlan. And Cesário!!!	evan / mdh & lh
Rhythms		22/11/2017	O.K. by Mark. O.K. by Lachlan. O.K. by Cope.	cope
Fixed Work	Copy editing and getting to Done		Done by Mark. Cope says Done. And Lachlan.	mdh
Patlets Appendix	Kind of like in the Org Patterns book		Significant progress made. BookBinder updated and most patlets framed out. Missing about a dozen patlets — June wiill work issue.	jk, cope
Approach Publishers		It's important to not do this too early, as it destroys credibility with the publisher if we bring a draft manuscript ("MVP") and then spend months readying the product.	In progress. Mail sent to VanHaren 28. sep. Mail sent to Jeff's publisher (Roger Scholl, Crown) 29 October. Author request to Productivity Press on 11 November. Book proposal sent to Productivity Press 20 November. Mail to Birgit at Wiley 21 November.	cope
Preface	A nice Zen preface		In progress. Comments solicited from Lewis Wilson.	cope & kh
Add Set-Based Design to the language			Depends on finishing up Visible Status.	cope
Involve the Managers	Copy editing and getting to Done		Rework in progress	lh and mdh
Circle of Trust	Copy editing and getting to Done		In the language, is not a good setup for Conway's Law.	lh and hdf
Product Organization Sequence	Is maybe good for now. May change if we eliminate Involve the Managers. But it does merit another pass over it.	End of August 2016 / 30/10/2017	Cope is captain. Did some repair because of bug in possessives in names.	nbh cope
Section on ROI?	That ROI can be any kind of value.		Motivated by June Kim question in EMail	cope
Core Scrum Sequence
Discussion: Do we need "PO also implements"?	Alexander hates hands-off architects. In Jeff Sutherland's team the PO builds running prototypes to keep their hands dirty.
Historical References in patterns	Good patterns tell where the idea evolved from		Mark pointed this out: See https://www.agilealliance.org/agile101/practices-timeline/
Audit: Pattern Recognisability	We need to audit the patterns to ensure that they are not just documentation of some part of Scrum, but that they can be indexed by the problem they solve to help Scrum teams gain insight to concrete problems			TBD
Audit: Pattern Context Linking	The patterns should flow as a language and should complete each other in a way where the flow between a pair of patterns is explicit and obvious. This needs to be audited and most patterns will need updating	Has to wait for a plenary session at next PLoP (Iceland?)	Depends on Sequences, which might help shed some light on doing this. Also needs to be coordiinated with "Create Pattern Language Graphs" (below)	team
ScrumPLoP things	1. Pictures / 2. Difference between self-managing, autopoeietic, autonomous		Ongoing...
Audit: 3 uses	Make sure each pattern points to three independently discovered known uses using citable sources.	Has to wait for a plenary session at next PLoP (Iceland?)	Currently being done incrementally	team
Audit: Is the PO the bad guy?	We don't want the patterns to portray the PO as the bad guy.			DF
Audit: Software focus	Needs to generalise beyond software
Book Picture Selection	We can use the stuff from presentermedia.com or the ones that Neil found from the LOC or...	Is progressing, but we probably should be starting to get explicit copy permissions. Need to check with publisher about what is needed.	"Done" includes having copy rights. Does it depend on having a financial framework in place?	nbh, mdh
Create Pattern Language Graphs	We need graphs like the ones in the Org Patterns book to orient people to the patterns and their relationships. Again can use the dag or dotty facilities. Google has facilities to make these "touchable" for the web deliverable		BookBinder part is done. Still need Organisational Structure Pattern Language graph.
Scrum Blitz scheduling	We'll need at least one Scrum Blitz to finalize "Overall copy edit" as well as the Audits		One done in the second week of 2017. Another scheduled for Lisbon before Scrum PLoP. Should have two more.	cr, nbh, mdh, lh, cope
Overall copy edit	Revisit patterns that haven't been touched in years, and make sure patterns reflect our current understanding and the current state of Scrum (the Scrum Guide has changed since we started)	4 of the team members concur that this is a 50- to 150-day job, full-time (½ - 1 day per pattern or other section; parallelism dscouraged). aa predicts end of June for his independent effort	Is being done as a team at a ScrumBlitz. Rate is about half the time of the estimate. / aa prediction was not met, and no update.	cr, lh, cope, mdh / aa removed as unengaged / nbh removed as disengaged
Legal and financial framework	We need a sink for the book royalties under a tax-free dispensation. It would be good if we also could be relieved of the adminstration.		We could maybe use Hillside as the administrator of these agreements	Check with Joe Yoder
Bring existing Scrum PLoP agreements up-to-date	The legal and financial framework will change the parties named in the Scrum PLoP agreement. The agreement must be updated and all signatories must sign off.		Depends on "Book legal and financial framework"
Professional copy-edit	It would be good to choose our own copy editor to bring the English quality up to publication standards. Past performance by publishers' copy editors has been of irregular quality		Depends on a funding source and "Legal and Financial Framework." Could be deferred until after the Alpha book, but that creates an uncomfortable ménage à trois with the publlsher and weakens our negotiating position
Alpha Book	A toolset that allows us to produce an alpha version of the printed book, along with enough topical content to make it interesting. Depends on book design / outline. / This is a benchmark and not an MVP. MVP doesn't apply to books and probably not at all in Agile: q.v. Luke Hohmann	7/1/2018	There is a risk to this effort if we convert toolset mid-stream	cope
Audit patterns against the Scrum Guide	We want to make sure we're not blindsided by missing something important in Core Scrum			df
Content audit	To make a conscious decision to discard certain patterns, create a few new ones to fill holes, and to keep the rest
Execute copyright transfer agreements	We will need to negotiate and execute a copyright transfer agreement with each author
IP Work	Citation verification; getting permissions for quotes
Art work	All art work needs to be re-done; each art design should be reviewed.
Layout	This needs to be done in collaboration with someone from our side to meet pattern community standards
Book Production
Book Publication		4Q2018
Android pattern app	An app that would allow people to reference the pattern languages and to augment them with local adaptations, or to combine patterns into an organizational Whole, in the spirit of Alexander's GateKeeper. First target should be Android: Canalys notes tht 51% of app downloads are Android downloads while only 40% are iPhone downloads. Kantar puts Android phone sales growth at 51.2% and iOS at 43.5%. In the embedded base there are about 900 million Android devices out there and only 600 million iOS devices (ALL - including iPhone, iPad, etc. — data from Flurry.) The app should be done in conjunction with a publisher, who will share in the revenue stream, to avoid copyright tranfer complications and to enlist the support of a publisher in coordinated release and marketing.	4Q2018
Emergency Procedure	Copy editing and getting to Done	08/10/2017	Mark says Done. Lachlan says Done. Cesário, too.	cope
Illegitimus non Interruptus	Copy editing and getting to Done	09/10/2017	Lachlan says Done. Mark, too. Cesário, too.	cope
Product Owner Team	Copy editing and getting to Done	23/10/2017	Lachlan says Done. Mark votes Done. And Cope says Done.	cr
Product Owner	Copy editing and getting to Done	23/10/2017	Mark says Done. Cesário says Done. Cope says Done. And Lachlan.	cr
Development/Delivery Team	Copy editing and getting to Done	24/10/2017	Cope says Done. Lachlan says Done. And Cesário. And Mark.	mdh
Daily Scrum	Remove ambiguities	25/10/2017	Lachlan says Done. Cesário, too. And Mark.	cope
Norms of Conduct	Copy editing and getting to Done	28/10/2017	Done by Mark and Cope. And Cesário.	lh
Question: Do we want to include the Harrison / Coplien patterns in the book or just reference them?	The book should stand alone but it could get pretty large if we include all the patterns we cite. Maybe just set up a spot on the web? Include half-page patlets for each, together with the quintessential photo?	26/10/2017	Having new patlets helps. Am inclined to stop at that. Picture pages are gone	team
Firewall		These seem to go together with the one resolved 2017/10/26. Nicked 2017/11/02.	Editors need to decide how to handle Organizational Patterns here	nbh / cope
Gatekeeper		These seem to go together with the one resolved 26/10/2017. Nicked 2/11/2017.	Editors need to decide how to handle Organizational Patterns here	nbh / cope
Patron-Supported Understanding	Scrum does not have buy-in from management. Therefore: Solution : Educate, get a patron and show result	15/10/2017		jeos
Historical Retrospective	Projects too often re-invent the wheel; Therefore: Start each new project with a retrospective over similar historic projects	15/10/2017	Relates closely with Learning Register	cope
Learning Register	Aggregate retrospective results into a collection of foundational, long-term learnings (from PRINCE2)	15/10/2017	Relates closely with Historical Retrospective	cope
Automated Code Checks	Definition of DONE does not mean: "Ready to Ship." Solution: Work on automating checks of the code.	15/10/2017	A bit software-specific. Generalize and relate to Toyoda looms? Stop-the-line? Subsume by DoD?	jeos
Rechunked PBIs	It's tedious to have too many fine-granularity PBIs deep in the Product Backlog; Therefore: Re-factor them back together into larger items	15/10/2017	Ville Mäkinen	cope
Down Time	How do you support the long-term vision and give the whole team a sense of buy-in? Therefore: Fund periodic time for the team to innovate.	15/10/2017		cope
Hackathon	Problem: Organisations become fixated on building to the business model and not allowing enough time for freedom of creativity. Solution: 24 hour hackathons quarterly, both internal to the organisation and external.	15/10/2017		gabby
External Feature Owner	Problem : Team is dependent an an external resource in the sprint and is unsure of how it is going. Solution : Make a team member responsible for the external resource, being proactive	15/10/2017		jeos
Rotating Guru		15/10/2017		Monica Yap
Definition of Done as Workflow	Team members must adhere to "Done" but also have to get their work done. Therefore: Integrate "Done" with the process, so the process tends to create results that adhere to the definition.	15/10/2017	New	vr
New Team Bootstrap	How to get a new team prepared to become a Scrum team	15/10/2017	Probably needs a lot of work	vr
Project Management	Scrum handles one product at a time, but you may have several revenue streams; Therefore: Handle several projects on a single product backlog	15/10/2017	Needs better name	cope
Team by the Side	The first team would have been well trained and well funded, the second and later teams would usually not get the same level of support. Therefore: Place a new team by the side of the existing Scrum team.	15/10/2017	This seems maybe to be a BBOM pattern	kh
Documentation, by the people for the people	Documentation is difficult to make useful to those who need it, and difficult to get from those who write it. Therefore: let those who need the documentation write it	15/10/2017	New	gabby
Improvement Community	You have a vision for change about how other teams do their work, to better cooperate with your own team or to improve overall system performance, but its not clear how to go about it. Therefore: Two or more Teams agree to work through system level problems together; each Team elects a member to represent them in an Improvement Community and consents to follow the agreements made by the community.	15/10/2017		Evan
Electric Field		15/10/2017	New	Evan
Are We There Yet?	It's hard to know if you're doing what you say you're doing. Therefore, create a “scorecard” for Scrum Teams to periodically fill out that checks to see how Teams are using the agreed on Roles and Policies.	15/10/2017	New	Evan
No More Rationalizations	Teams rationalize their impediments, which can impede progress. Therefore: Have each team work rationalized impediments with the Product Owner.	15/10/2017	New	Evan
Consilience Team	Hackathon	15/10/2017	New	Evan
Working Agreements	Is this Cesário's pattern, that we've already done?	15/10/2017	New	Evan
Coherent Theory		15/10/2017	New	Evan
Bumper Bowling	It's tempting to do Scrum in a way that doesn't work. Therefore: have a deeply experienced ScrumMaster encourage a bounded direction for team evolution and growth.	15/10/2017	New	Evan
Definition-of-Done Baseline	It's common to set the bar too high or too low for the definition of Done. Therefore: Set the definition of "Done" according to how most team members do their work.	15/10/2017	Probably lacking QWAN. Need to review	vr was editor. Editors should review.
Product Pride			DUPLICATE - Deleted	gb
Linking Patterns into Languages	We need to develop a graph of containment relationship between the patterns, do a cluster analysis into languages, and to refactor the patterns so they are cohesive within each of their language contexts. Estimated amount of time: 1 staff-year	3Q2016
Work the Top of the Backlog	Pattern on working the top of the backlog (破)		破. Cp. First things First, Swarming,	js / cope — Ping Jeff about what we should do with this
Bake-Off	Set-based design		Replaced by Set-Based Design	cope
System Level Definition of Done	You want uniform quality across teams with regard to certain quality criteria. Therefore: define a system-wide definition of Done that applies to all teams.	Status changed 2015/06/07	Dropped	vr
Writing "Glue"chapters	We need some lightweight glue chapters describing how to use the patterns, including descriptions of sequences (which is a separate PBI), language semantics, interaction between the languages. Also includes Introduction.		Broken down into other patterns
Writing supporting chapters	Patlets, indices, pattern language diagrams,		Broken down into other patterns
Helpers in Pairs	See Pattern Description	01 July 2014	Seems to be a BBOM pattern. We can resurrect it upon further review.	kh
Question Hour			Time analog of Snack Shrine. But this seems not to have much QWAN, and I think the necessary situations are already handled by other patterns. See the notes on the pattern itself in Works in Progress.	vpe
Watchdog	ScrumMaster pattern	8/1/2015	New	nbh
Emergency Procedure	Sometimes unexpected work arises during the Sprint, and there are regular rhythms in how to address them; Therefore: Define levels of escalation that resolve emergencies in the least disruptive form of escalation possible	8/1/2015	Needs to be put into Alexandrian form. No new workshop.	js / nbh (to put in Alexandrian Form)
Information Radiator	Scrum's process of Kaizen depends on transparency and visibility. Create information radiators (charts, boards, roles) to keep information in the face of the team		Kind of an umbrella pattern. Take bits from Radio Product Owner, many others.	Lachlan will clean up
Cleanup on Conway's Law	A more refined version of the classic	10/22/2014		cope
ScrumMaster Coach (needs cleanup by Cope)		10/22/2014	Coaches shouldn't coach teams but should coach ScrumMasters. I'd like to see a lot of the coaching patterns folded into this one	Evan
Clean up Sprint Backlog Item		10/17/2014		cope
Regular Product Increment	You need useful measures of gross development progress. Therefore: Therefore; a product increment must be regularly developed in a time box (no longer than a Sprint).	10/17/2014	Maybe needs re-framing for Value Stream pattern language	lh
Fixed Date PBI	Some PBIs aren't scheduled by the PO, but reflect external dependencies or personal events such as vacation, or scheduled courses, conferences or vacations.	10/17/2014	Needs another workshop; no major changes anticipated.	cope
Resolve conflict / combine Norms of Conduct and Working Agreements		10/17/2014	Either differentiate these patterns well or combine them into one pattern. Conclusion (from Evan): Old, and subsumed by other things	Evan & cesário
Sprint Backlog Item	See Pattern Description	10/17/2014	Bring pattern to Done, based on WW comments	df / Abandoned
Visible Status, Burndown Chart, Scrum Board; ties in with Information Radiator, above	One pattern or three? The Swarm should figure this out and write the right patterns	10/17/2014	Consider discussing and making a decision at a ScrumBlitz	nbh
ScrumMaster Turns Into a Chicken / ScrumMaster Incognito	Problem : Team member look at SM during Daily Scrum Solution : SM goes away from the inner circle and become a chicken	10/16/2014	Needs Sketch. Needs to be revised to be put in Alexanderian Form	jeos / df
Daily Scrum	Because we have emergent requirements and uncertainty, the Development Team replans dailly to raise the chances of meeting their forecast.	10/15/2014	Workshopped at ScrumPLoP 2013. Awaiting revision	NBH, LH, cope'
Norms of Conduct	A team is unable to discuss issue; things are unsaid, questions are unanswered, and solutions are not explored; Therefore: create norms of conduct to promote constructive conflict and discussions.	9/19/2014	Needs sketch	cr
Create Knowledge	As the number of teams using Scrum grows they will face impediments and create valuable knowledge on solving them in their specific setting. Therefore: Form optimization teams consisting of people from the various Scrum Teams to capture the created knowledge so that the teams and organization can learn from it.	9/19/2014	Needs Sketch. No new workshop.	cr
Enduring Change	Teams left to themselves fall away from Scrum. Therefore: by putting upper and middle management support in place and empowering the teams to define impediments, the organization becomes self-sustaining.		New	Evan
Fire Keeper	Teams need to surface and deal with tacit fear, but raising fear can breed fear. Therefore: create a role, like the ScrumMaster, to hold team fears and hold them in an objective light.		New	Evan
Governance Meeting	You need a place to come together to resolve tensions. Therefore: create a governance meeting as a time and place for focusing on the organization's tensions.		New	Evan
North Star	It's easy to get lost in details and local optimizations during development-level Kaizen. Therefore: have the Product Owner establish the vision of the big picture to rally the team to a concerted direction.		New	Evan
Prepared Environment	While executive management may push Scrum, they're too far removed from the troops to support them. Therefore: form a middle management team whose job it is explicitly to support the Scrum transition at the grassroots level.		New	Evan
Stable Bases	What does it mean to work on tensions from the Impediment list: Publish a document describing the team's work at resolving tensions.		New	Evan
Teams Raise Tensions	How do teams self-organize while retaining access to governance records? Give the team direct access to the Product Owner and the tension backlog.		New	Evan
Tension Backlog	Discussions about problems and direction can go on forever. Therefore: create an Impediment List to structure the team's discussion.		New	Evan
Break Eye Contact			Overlap with Hide the Chicken?	gpb
Constant Crisis				gpb
Singular Mediator				vpe
History of the Patterns	Review, copy edit, get to Done	26/09/2017	Cesário says O.K. Mark says O.K. And Lachlan.	dina & cope
Follow the Moon	Scrum cycles should be attendant to natural rhythms (破). Needs copy editing and getting to Done	04/09/2017	Cesário says Done. Cope too. And Mark. And Lachlan.	gb
Small Red Phone	Copy editing and getting to Done	11/09/2017	Cope says Done. And Cesário. And Mark.	lh
Scrum(Master) Coach	Has never been workshopped?	11/09/2017	Cope says Done. Cesário says done. And Mark.	lh
Sauna Sprint Review	People need motivation; therefore, celebrate success with an extended sauna and champagne		Seems already to be covered as an example in the Sprint Review pattern yes — dropped	cope
Conversion of the Development Team and ScrumMaster pattern languages (our most complete languages) to the new environment			Environment needs to be established first. / Dropped, because there will probably not be a "new envioronment," and the patter languages have changed.	aa
Conversion of other pattern languages (other than Development Team and ScrumMaster) to the new environment			Environment needs to be established first. It would also be good to first convert the two named pattern languages since they're pretty complete / Dropped, because there will probably not be a "new envioronment," and the patter languages have changed.	aa
Pulse	Uncertainty about the duration of a work episode prevents the work from being done effectively, so work in time units of uniform length		15 July 2016 / Probably delete — more of a meta-pattern than a pattern. / Not in the book outline. / Lachlan says delete. Cesário, too. And Mark.	nbh / cope
Sacred Schedule	If you don't end on time, you don't know where you are; Therefore: Don't put off Sprint completion, even for a day.		Probably needs to be re-thought, or just folded into Sprint. / Not in the book outline. / Lachlan says delete. Cesário, too. And, finally, Mark.	cope & nbh
ScrumMaster Incognito	Copy editing and getting to Done	15/08/2017	Mark says Done. Lachlan, too. And Cesário.	dina & cope
Stable Teams	Copy editing and getting to Done	22/08/2017	Cope says Done. Mark, too. And Cesário. And Mark.	lh
Kaizen Pulse	Copy editing and getting to Done	22/08/2017	Done according to Cesário. Cope says done. Mark, too. And Lachlan.	cope
Happiness Metric	Copy editing and getting to Done	01/09/2017	Mark Cope is Captain. Lachlan says done. Mark, too. Cesário, too. Should still cite example frome Verwijs's work.	cope
Swarming	Copy editing and getting to Done	01/07/2017	Near by Mark.	cope
Scrum Team	Copy editing and getting to Done	28/08/2017	Lachlan is captain. Cope says Done. Mark, too. Awaiting Cesário.	lh
MetaScrum	Copy editing and getting to Done	01/07/2017	Cesário is Captain	cr
ScrumMaster	Copy editing and getting to Done	02/07/2017	Cesário is Captain.	cr
DoneMaster	Copy editing and getting to Done	02/07/2017	May eliminate.	cr
Knight of the Mirrors	Copy editing and getting to Done	02/07/2017	May eliminate.	cr
Sheepdog	Copy editing and getting to Done	02/07/2017	May eliminate.	cr
Coach	Copy editing and getting to Done	02/07/2017	May eliminate.	cr
Cheerleader	Copy editing and getting to Done	02/07/2017	May eliminate.	cr
Product Owner Trainer	Has never been workshopped? Propose eliminating.	02/07/2017	May eliminate.	cr
Cross-Functional Team	Copy editing and getting to Done	02/07/2017	Lachlan says to deal with this during the Blitz. Done during the blitz.	lh
Sequence to knit together patterns related to organising multiple Scrum teams / ----------- / Scaling Sequence	How do we give visibility to the patterns that deal with an organisation that has more than one Scrum team per product? / -------------------------- / We need to evaluate whether the scaling sequence will fit together with the new Value Area pattern(s) and, if so, write it	30/06/2017		aoc? cr
		30/06/2017	CR is captain. First draft done. Yay! AOC et al. are refining. Cope says Done.	aoc
Conway's Law	Copy editing and getting to Done	30/06/2017	ScrumBlitz	—
Organizational Sprint Pulse	Copy editing and getting to Done	30/06/2017	Cope is captain. Ready for review. Lachlan says Done. Mark says Done. Awaiting Cesário.	cope
Set-Based Design	To evaluate potential alternative product directions, hold a "bake-off"	30/06/2017	Evan has wrapped up. Ready for review. Processed at Scrum blitz.	evan
ScrumMaster Gets Fired	Has never been workshopped?	04/06/2017	Dropped
Notes on Velocity	Copy editing and getting to Done	11/06/2017	Cope is captain. Ready for review. O.K. by Cesário. Mark votes Done. Lachlan's comments accommodated.	cope
Greatest Value	Copy editing and getting to Done	11/06/2017	Cope is captain. Ready for review. Lachlan says Done. Mark says Done. Have accommodated Cesários comments.	cope
Heavily caveat Change for Free	Change for Free depends on a much tighter context than is currently in the pattern	12/06/2017	Gabby originally motivated this. Awaiting her comments.	cope
Self-organizing Teams	needs to describe how local interaction leads to the roles of SM, PO, Dev team - this is for the product organisation sequence - unless we mean self-organising = self-managing (noted by Lachlan)	30/06/2017	Lachlan is captain. Cope says Done. Mark, too. Cesário, too.	lh
Development Partnership	Probably done. Reviewed at Scrum PLoP 2016	30/06/2017	Cope is captain. Ready for review. Lachlan says Done. Mark says Done. Cesário, too.	cope
Small Teams	Copy editing and getting to Done	30/06/2017	Mark is captain. Lachlan says Done. Cope says Done. Cesário too.	mdh
Collocated Team	Copy editing and getting to Done	30/06/2017	Mark is captain. Cope says Done. Lachlan says Done. OK by Cesário.	mdh
One Step at a Time	Copy editing and getting to Done	30/06/2017	Turns out this is reallly important. Done and ready for review. Lachlan says Done. Mark says Done. Waiting for Cesário.	cope
Generalize Scrum of Scrums	Not just "a representative from each team," but ad-hoc attendance as needed	30/06/2017	Helps collapse neo-scaling sequence. Cope says Done. Lachlan, too. And Mark. Awaiting Cesário.	aoc
Fixed Date PBI	3 known uses audit still fails	02/05/2017		Editorial Team
Product Pride	Copy editing and getting to Done. Enlist Gabby — she once proposed a pattern like this.	04/05/2017		gb
Regular Product Increment	Copy editing and getting to Done	04/05/2017	Lachlan is Captain. Cope says Done.	lh
Clarify difference between Whack the Mole and Good Housekeeping	"Aiming" to have a result is a KPI, not a pattern. The cadence aspect of DCC is nonetheless nice. Both should probably be retained but both probably need some cleanup.	03/05/2017	Mark is Captain	lh / mdh
New Good Housekeeping	Old one needed redoing	04/05/2017	Quinta da Pacheca	lh
Mitosis	New Pattern (Scaling)	04/05/2017	Cope will captain	cope
Impediment List	Copy editing and getting to Done			mdh
Visible Status	Distinct enough from Information Radiator?	04/05/2017	Decided 'yes.'	Editorial Team
Remove references to non-existent patterns	Need to remove references to patterns that have been deleted or never written. There are about 28 at last count. BookBinder audits can automatically produce the lists but there will be local rewording in each pattern, and the overall flow and wording must be attended to.	1 October 2016. Delayed because we need to decide whether we'll need these patterns. / Done 5/2017 — last one was Four Minute Mile	Detailed data here	cope
Teams that Finish Early Accelerate Faster	Copy editing and getting to Done		CR is captain. LH has been very active. Mark says Done. Cesário, too.	Editorial Team
Dependencies First	Copy editing and getting to Done		Cope says Done. Lachlan says Done. Cesário, too. And Mark.	lh
Oyatsu Jinja	Copy editing and getting to Done. Needs minor language cleanup.		Lachlan is captain. Cope says Done. Mark, too. Cesário had one light comment that I think we can live with.	lh
Responsive Deployment	Copy editing and getting to Done		Cope is captain. Ready for review. Césario says O.K. Lachlan, too.	cope
Firewall	Not sure why this is here. Placeholder for now.	07/05/2017	Eliminated from chapter.
Surrogate Product Owner	Copy editing and getting to Done	07/05/2017	Deleted.
Sprint Goal	Copy editing and getting to Done	04/04/2017	Mark is Captain. Cope says Done. Cesário says Done. Lachlan says Done.	Editorial Team
Product Wake	Copy editing and getting to Done	01/05/2017	Mark is Captain. Cope agrees Done. And Lachlan. And Cesário.	Editorial Team
Birds of a Feather	Writers' Workshop, copy editing, getting to Done	01/05/2017	Now has good header picture. Orphaned. Cope has wrapped it up and put out a call-to-Done. Lachlan says Done. Mark had suggestions that I don't think are needed. Cesário says "Done" and had a side comment.
Sprint Backlog Item	Copy editing and getting to Done	01/05/2017	Mark is Captain. Cope says Done. Lachlan says Done. Cesário says Done.	Editorial Team
Updated Velocity	Copy editing and getting to Done	21/04/2017	Cope will captain. Incorporated Lachlan's comments. Mark says O.K. Cesário says O.K.	cope
Small Items	Copy editing and getting to Done	Lachlan is Captain. / Done 21/4/2017	June and Alan have commented that it needs some work because of overlap / potential confusion with the SBI pattern. Cope thinks Done. So do Mark and Cesário.	lh
Whack the Mole	Copy editing and getting to Done	28/04/2017		lh / mdh
Spirit of the Game	Still needs some minor cleanup.	28/04/2017	Mark is Captain
Team Sprint	Copy editing and getting to Done	28/04/2017	Mark is Captain	Editorial Team
Scrum of Scrums	Copy editing and getting to Done	28/04/2017	Cesário is Captain. Cope says Done.	cr
Leading Team	New Pattern (Scaling)	28/04/2017	Cesário will captain	cr
Product Backlog Sequence	At least it would be another example sequence	29/04/2017	Cope is Captain. Mark says O.K. Ditto Lachlan.	cope
Value Stream Fork	Probably done	29/04/2017	Cope will captain. Tentatively ready for review.	cope
Tie up Value Areas	In particular Value Area seems to extend Scrum or portray an alternative vision to Scrum, in areas that seem already to be covered by the Meta-Scrum, Independent Velocities, and Scrum of Scrums.	29/04/2017	Cesário will captain	cr
High Value First	Copy editing and getting to Done	01/05/2017	Cope is Captain. Mark agrees Done. Cesário DISAGREES.	Editorial Team
Four Minute Mile	Retired.			gpb
Missing Description for FireWall placeholder		02/03/2017	Re: Mark. Removed to external patterns and references updated.	cope
The Mist: Needs Sketch		06/03/2017	Prototype done	cope
Production Episode: Needs Sketch		06/03/2017	Prototype done	cope
Small Items: Needs Sketch		05/03/2017	Tentative prototype done; & done	cope
Estimation Points: Needs Sketch		06/03/2017	Prototype done	cope
Sprint Review: Needs Sketch				mdh
Change for Free	Copy editing and getting to Done	26/01/2017	Cope is Captain. Mark says Done. Lachlan says: Pretty much O.K. Cesário abstains.	Editorial Team
Update BookBinder for site port to generic hosting site	Google Pages / Sites is about to undergo major change, which may be incompatible with how we're doing things. We need a Plan B.	01/04/2017	Will take a good deal of research and experimentation. Don't know if we'll convert when done because WYSIWYG editing will go away. But we'll have a portable web representation of the book and a high probability of BookBinder compatibility.	cope
Daily Clean Code / Good Housekeeping	Copy editing and getting to Done: (Title Change)	19/03/2017	MDH LH is Captain. Mark considers it Done. Lachlan too, apparently. And Cesário.	Editorial Team
New head picture for Testable Improvements		21/03/2017	Cope has a candidate. Mark approves.	cr / mdh
Developer-Ordered Work Plan	Copy editing and getting to Done	22/03/2017	Sketches have been updated completely. Cope pronounces done. Lachlan says O.K. Mark does, too.	Editorial Team
BookBinder picture manifest	Have BookBinder generate a picture manifest for use by publishers	25/03/2017	Done	cope
Autonomous Team	Needs to refer to Scrum Team rather than Development team (or both teams) (noted by Lachlan). Needs sketches.	26/03/2017	Cope is Captain. Done candidate. Mark and Lachlan say Done.	cope
Production Episode	Copy editing and getting to Done	28/02/2017	CR is Captain. Cope agrees done.	Editorial Team
Testable Improvements	Copy editing and getting to Done	04/01/2017	CR is Captain. Cope agrees done. Mark agrees text is done. Lachlan too.	Editorial Team
Sprint Retrospective	Copy editing and getting to Done	28/02/2017	MDH is Captain. Mark, Cope & Cesário pronounce Done. And Lachlan	Editorial Team
Need old picture back in Illegitimus non Interruptus			It matches the pattern too well.	mdh cope
Chief Product Owner is an "alias" for Product Owner Team	Chief Product Owner is in the normal flow of patterns as an alias for Product Owner Team. Having two names for the same pattern is confusing. Maybe just list the alias under the pattern name?		Re: Mark. Probably change references to CPO to refer directly to PO team with an s.v. re: CPO.	cope
Putting BookBinder under git	To facilitate sharing with Ademar and to ensure there is a backup	22/02/2017		cope
Stop-the-Line an "alias" for Emergency Procedure			So it's still an alias but the alias no longer has its own page. Alias added as subtitle on pattern page.	cope
Release Staging Layers	Copy editing and getting to Done	27/02/2017	Cope is Captain. Sketches done. Mark, Lachlan and Cope vote "Done". And now Cesário.	Editorial Team
ROI (Rename to ROI-Ordered Backlog)	Copy editing and getting to Done	25/01/2017	Cope is Captain. Renamed. Sketches drafted. Lachlan, Mark and Cope say "Done". And Cesário.	Editorial Team
Release Range	Copy editing and getting to Done	19/02/2017	Cope is Captain. Sketches drafted in (electronic versions; need to be drawn). Lachlan and Cope say "Done." So does Cesário. And Mark.	Editorial Team
Money for Nothing	Copy editing and getting to Done	24/02/2017	Cope is Captain. CR blesses. Lachlan too. And Mark.	Editorial Team
Definition of Done	Copy editing and getting to Done	04/01/2017	CR is Captain. Mark and Cope pronounce "Done". Lachlan approves. And CR.	Editorial Team
Sprint Review	Copy editing and getting to Done	04/01/2017	CR is Captain. JOC thinks it is done (still needs sketches). And Mark. And Lachlan.	Editorial Team
Chapter 1	Writers' Workshop, copy editing, getting to Done		Initial Draft. Done for now.	lh, cr, cope, aoc
BookBinder updates to flag bad URLs	Some URLs that point to patterns point to the wrong place. BookBinder can use its BookFiles table to audit this	03/03/2017		cope
BookBinder updates for section cross-references	Pattern cross-references work find but we need something for chapter and section headers	06/02/2017		cope
HU BookBinder processing	So we can start working on Dedications, Acknowledgements, etc.	20/02/2017	I think this works.	cope
Yesterday's Weather	Copy editing and getting to Done		Lachlan is captain. Cope agrees done.. So does Cesário. Mostly Mark (wants satellite example).	Editorial Team
Team Pulse as alias for Regular Product Increment — how to handle aliases	Team Pulse is in the normal flow of patterns as an alias for Regular Product Increment. Having two names for the same pattern is confusing. Maybe just list the alias under the pattern name?	27/01/2017	Re: Mark. Deleted the alias in the outline.	cope
Sprint	Copy editing and getting to Done	29/01/2017	CR is Captain. Sketches are on their way. Needs consistent citation work.	Editorial Team
Removed Spike	Also removed references in Fixed Work, Product Owner Team	15/01/2017		Cope
Definition of Ready	Copy editing and getting to Done	Done 9/1/2017	Cope is Captain / Now has sketches	Editorial Team
Granularity Gradient	Copy editing and getting to Done	Done 7/1/2017	Cope is Captain. Has sketches.	Editorial Team
Fixed Date PBI	Copy editing and getting to Done	Done 6/1/2017	Cope is Captain / Has Sketches	Editorial Team
Vacation PBI	Copy editing and getting to Done	Done 6/1/2017	Cope is Captain. Has sketches.	Editorial Team
Enabling Specification	Copy editing and getting to Done	Done 5/1/2017	Cope is Captain. Has sketches	Editorial Team
Aggregate Velocity	Copy editing and getting to Done	Done 6/1/2017	MDH is Captain	Editorial Team
Specialized Velocities	Copy editing and getting to Done	Done 7/1/2017	MDH is Captain	Editorial Team
Sprint Backlog	Copy editing and getting to Done	Done 5/1/2017	CR is Captain	Editorial Team
Scrum Board	Copy editing and getting to Done	Done 5/1/2017	CR is Captain / Has Sketches
Sprint Burndown Chart	Copy editing and getting to Done. Needs new picture for the chart itself.	Done 5/1/2017	CR is Captain
Track Done	Copy editing and getting to Done / Removed and folded into Sprint Burndown	Done 5/1/2017	CR is Captain
Information Radiator	Copy editing and getting to Done	Done 5/1/2017	CR is Captain
Pigs Estimate	Copy editing and getting to Done	Done 5/1/2017	MDH is Captain
Estimation Points	Copy editing and getting to Done	Done 5/1/2017	MDH is Captain
Running Average Velocity	Copy editing and getting to Done	Done 6/1/2017	MDH is Captain
Fix mura (斑) rendition	When 斑 appears a parenthesis gets eaten	Done 8/1/2017		cope
Fix "à" translation bug	The "à" character causes unlexable HTML metacharacters to enter the flow	Done 8/1/2017		cope
Product Backlog	Copy editing and getting to Done		Still can finesse the header picture. We'll leave this to the efforts Mark is coordinating
Remove author names from patterns	Mark has identified 16 patterns that still have author affiliations. Most of them (except references to third-party authors) should be removed	Cope took a shot at this 8/1/17. Should be double-checked. Mark double-checked. Done 9/1/17.	Detailed data here
Release Plan	Copy editing and getting to Done	9/1/2017	MDH is Captain	Editorial Team
Spikes	Sometime you need (perhaps arbitrarily time-boxed) activities whereby the Development Team helps the Product Owner clarify requirements	July 2016	Put aside for now. We can bring back a PO version if someone takes on the task of writing it, but the Dev Team version of it is dead. Try to refer to it in Set-Based Design	aa, df, vr, vpe
Remove the Shade	who does this [ie who removes the shade]? Who removes the hero? Perhaps change to “Remove the shade created by the hero” in solution (noted by Lachlan)		Took a shot at a fix 8/1/2017. See if it works now. / Done 16 January 2017	cope
Update BookBinder to process H1s with hyperlinks	Sections in the BookOutline should be able to link to separate pages for the content, as works for pattern references	1/23/2017	Makes it easier to edit the Outline chapter	cope
Rename Daily Clean Code	New name is "Good Housekeeping"	1/23/2017	Be attentive that references emphasize "daily" where appropriate	cope
BookBinder fix for §	§ symbol needs to make it through the flow from &#167; to \'a7 (ASCII code 176)	Fixed 18 December 2016	See Fixed Work for an example of the problem (in the header picture subtext)	cope
Scrumming the Scrum	Copy editing and getting to Done	18/11/2016	Has sketches.	Editorial Team
Product Backlog Item	Copy editing and getting to Done		Has sketches	Editorial Team
Refined Product Backlog (formerly Refined Backlog)	Needed as a pattern in its own right rather than as an alias for Definition of Ready. It's about having a backlog that is properly ordered with reasonable attributes on the PBIs.	14 Nov 2016	Done; ready for review	cope
The Mist	Copy editing and getting to Done			Editorial Team
Vision	Copy editing and getting to Done			Editorial Team
Value Stream	Copy editing and getting to Done			Editorial Team
Product Roadmap	Copy editing and getting to Done			Editorial Team
Meta-Scrum	I think we need this	Being reassigned	Done	al js
The Mist	Scrum Teams aren't created by the Scrum Fairy overnight but tend to emerge from human connections, growing energy, and a gradually congealing vision. Therefore: Nurture an environment where the necessary pre-work and evaluation can take place as the primordial soup from which Scrum teams emerge	End of August 2016	Came out of a discussion about Project Ready Criteria. Done for now; should be revisited on another pass.	cope
Release Plan	Copy editing and getting to Done			Editorial Team
BookBinder enhancement for picture link integrity	Links to pictures in */works-in-progress/* and */very-old/* should be flagged	I think this is done. PictureFile.m:217		cope
Meta-Scrum	Copy editing and getting to Done			cope
Development Partnership	We need to say somewhere where to put the PO in a Vendor / Consumer relationship. Maybe a new pattern: Partnership? Is this Terry Funino-san's old Confederation pattern?	End of August 2016	Reviewed at Scrum PLoP 2016, awaiting revision. Tentatively done; should come back to it to make sure.	cope
Out of the Mist	New pattern that extends the Mist into the other PLs	End of August 2016	Removed. I think that Vision fits the bill, and a reworking of The Mist to fit Vision makes this go away.	cope
Quantum Entanglement			Picture added 29/8/2016	gpb
Value Stream Sequence		Done		cope
Responsive Deployment	Sometimes the market demands instananeous response and you don't want to wait until Sprint Review. Therefore: Let the PO review a PBI in the middle of the Sprint and ship immediately	Done 9 July 2016	Renamed from Continuous Deployment. Needs stripping down and editing	cope
Value Stream Fork	A product can get only so big before it can't adeptly deal with market feedback. Therefore: at a certain point, split the product into multiple products	May 2016	Tentatively done; should revisit	cope
Core Competencies	Core competency is embodied in the organizations that form around them	Dropped	Standards for Improvement Consilience Team, etc. Dropped per Cesário's Email of 5 June 2016	Evan and Cesário
Book "design" / outline	The "product" is a table of contents	5/25/2014	I think all the details have been resolved, and we have a working book design	team
Substitute in Daily Scrum		Dropped	Needs a sketch. Has it been workshopped? / ------------------------- / Dropped	vr
BookBinder extension to deal with dot files	Needed to display graphs, such as for pattern languages, in the text		Beta version done	cope
BookBinder not properly identifying non-pattern section headers		Done 20 June 2016		cope
Product Wake	All good things must come to an end		Workshopped in Porto 2016; done	cope
Audit: Scrum-centric or general Agile?			It's going to be Scrum-centric.
Catalyst	Create an environment in which team members want to come together to communicate and collaborate, as well as provide opportunities for them to come together.	Deleted — Porto 2016	The pattern solution seems to be about the environment rather than the SM's role in facilitating it. I think the environment role is important but that the SM's role in shaping it is maybe overstated	cope & nbh
Round Robin Status	It is easy to focus what you are working on, and neglect the rest of the team; Therefore: Each person in turn gives status.	Killed	Ready for Porto Writers' Workshop	nbh
Book title	I think we've settled on: "A Scrum Book."		Just need to confirm for now	team
Sequence Seminar	Get everyone on board to Alexandrian sequences		Done — Porto 2016	cope
Team Sprint	The Product Owner is sometimes too externally focused; Therefore: let team members occasionally take control of the PBIs that they want to do		Have case study from Gabby; just need to edit it in. Done.	Velu
Value Area	Scaling staff creates inefficiences and stresses the organisation: instead, divide and conquer	4/10/2016	Paul is unresponsive regarding his responsibility towards this. Finished by Cesário and then re-opened (separate item) as the scaling discussion opened up	Cesário / Paul
Velocity Chapter?	Velocity isn't a pattern but people will be looking for it, as a technique.		A draft exists. Needs review	cope
Product Roadmap	A Product Backlog is a path, at any given time, through a roadmap whose business alternative decisions have been bound. Roadmaps are still a good idea and their relationship to the Product Backlog is instructive. Maybe merge this with / use it to supercede Release Plan.			Sashimi Scrum Blitz
Definition of Done	See Pattern Description	9/18/2015		vr
Discussion on how to treat Scaling	We probably want a chapter on scaling. We should decide that and should decide on the tone of ther overall message we want to convey. Most of the sentiments so far have leaned more towards descaling than scaling.		I've roughed in a chapter where it could fit, but we need to socialise this, see if that's the right thing to do, and start building a platform / position	lh
Value Stream	The big pattern over the process elements			cope
Small Red Phone	Critical personnel should never be out-of-reach; Therefore: Give each one a cell phone as an ever-ready hotline to be used in emergencies		Low-hanging fruit	cope
Greatest Value	You want to reward good behavior at each level, yet you want the greatest value. Therefore: Let the vision drive to the value with the greatest scope.		Should Cope follow up with Mary Rettig?	js / cope
Small Items	Big items are hard to estimate; Therefore: Break down items so they are small enough to estimate with confidence	Try to get done for Porto!		nbh / cope
Impediment List				Originally owned by Gabby — hopefully she'd like to do it
Small Team	A large group of people working together will usually splinter into subgroups decreasing the overall group effectiveness. Therefore: Use small teams of people working closely together.			lh - will run with it
Cheerleader	The ScrumMaster challenges and motivates the team while sustaining morale			nbh
Chief Product Owner			Removed: folded into Product Owner Team
Product Owner Team			Needs cleanup and sketch
Snack Shrine	See Pattern Description	01 July 2014	Bring pattern to Done, based on WW comments	kh
Scrum Team		10 July 2015	Consilience Team (which was once competing with this one) is probably something different. We should put this one into a writing workshop in Porto.	lh
Burndown Chart				aoc
Scrum Board			Contrast with Kanban board	aoc
Estimation range	Estimation isn't just about accuracy, but also about precision; Therefore: Handle estimates as ranges. This is much better covered by using the pattern Release Range.			nbh
Google Pattern Page Parser	Eventually we'll need to render the book in some standard format as LaTeX, Word, or Frame. To do that we need to read in patterns and convert them. Having a parser for the arcane Google Pages format is a good starting place to make this happen	Done 11 February 2015		cope
Impediment Removal Team	Large impediments require large effort to remove. Who should do this work? Therefore: Create a Scrum team whose job it is to remove impediments.	19 January 2015	Fold into Scrum of Scrums; not a pattern in its own right.	Evan
Scrum Adapter (Transition Team)	Isolated Scrum teams have an uphill battle in front of them. Therefore: Leaders of the groups adopting Scrum should join together to create an organizational entity that wraps the Scrum Teams with an interface to the rest of the organization.	19 January 2015	If we have a "patterns process" chapter, this kind of material belongs in such a chapter, but not as a pattern in its own right.	Evan, Cesário? Jeff? Evan is Captain.
Transition Team (see Scrum Adapter, above in the backlog)		19 January 2015	A chapter rather than a pattern? Instructive for teaching people about the patterns?	Evan is Captain. Jeff, Beedle
Definition of Ready	If work items are not precisely understood, development effort (and time) tend to balloon, which in turn cause the Sprint to fail. Therefore, deefine criteria which items must meet before they can be put on the Sprint backlog.	1/6/2015	Workshopped at ScrumPLoP 2013. Awaiting revision. Should relate the points from Jeff's video. Neil will follow up.	nbh
Collocated Team	How do you maximise communication in a team and support the seemingly random nature of it? Locate the entire team within talking distance	1/20/2015	Workshopped at ScrumPLoP 2013. Awaiting revision	lh
One Step at a Time	See Pattern Description	01 July 2014	DONE, pending comments from other folks	df
Fixed Work	Some work must be done on the team, but is difficult to estimate a closed work item. Therefore: Compartmentalize both recurring work and occasional spikes of work, particularly those that support the Product Owner process instead of directly building potentially shippable product		Needs sketch. No new workshop	cope
Updated Velocity	You want the velocity to reflect the team's current abilities, yet it takes time to know whether process improvements actually worked; Therefore: Update the velocity only if a new level is sustained for the past three sprints.	15 June 2014	Done; needs sketch and sketch fix (language).	cope
Development Team	See Pattern Description	14 June 2014	Bring pattern to Done, based on WW comments	cope
Running Average Velocity	Calculate velocity as an aggregate of past velocities	01 July 2014	NBH needs to fix last line of Running Velocity to describe difference between the two. --> DONE	nbh
Circle of Trust	See Pattern Description	12 June 2014	DONE	nbh
Sprint Review	See Pattern Description	12 June 2014	DONE, pending comments from other folks	nbh
Testable Improvements	See Pattern Description	11 June 2014	DONE	nbh
Self-Organizing Teams	See Pattern Description	10 June 2014	DONE	nbh
Whack the Mole	See Pattern Description	08 June 2014	Bring pattern to Done, based on WW comments	cope
Dependencies First	See Pattern Description	01 June 2014	Bring pattern to Done, based on WW comments	cope
Scrum of Scrums	See Pattern Description	31 May 2014	Bring pattern to Done, based on WW comments	Cesário
Stable Teams	Teams can't get velocity unless they build mutual trust and familiarity. Therefore: keep teams relatively stable over time.	26 May 2014	Was workshopped many years ago. Needs cleanup. Needs sketch. It's probably done and we just need to get the most recent manuscript online	gb & lh. Cope is following up with the authors
Send "organising mail"	Mail to encourage people to take responsibility for Scrumblitzes and to scope what the Scrumblitzes will do	5/25/2014	Wait until Product Backlog is cleaned up
Portfolio Backlog	20% of the work generates 80% of the revenue. Therefore: focus on the big winners at the portfolio level, and create a priority list of projects.		New	dg
Radio Product Owner	There are many voices within an organisation with suggestions for what should go into the product, therefore, the scrum team needs to tune into the signal of the product owner, and ignore the rest of the noise.		Cited by other patterns. Fold into Information Radiator.	lh
Portfolio Standup	Large enterprises manage many projects, but the market and the world for those projects changes. Therefore: have weekly standups to groom the portfolio backlog.		New	dg
Project Ready Criteria	Unclear requirements are a common problem. Therefore: have "Ready" criteria that must be met before development starts.		New	dg
Sprint Retrospective	You need a focal point for process improvement, because true continuous improvement is inefficient. Therefore: Convene a periodic ceremony to focus on process improvement		Needs Sketch. No additional workshop.	nbh
Enabling Specification	Unexplored requirements cause unpleasant surprises; Therefore: The product owner should deliver enabling specifications that show that important questions have been raised and adressed		Needs sketch. No new workshop	js
Accountable Estimates	The Product Backlog must be estimated by the people who commit to the estimates. Therefore: have the Team develop cost estimates and the Product Owners develop Business Value estimates.		Can't distinguish from Pigs Estimate. Delete this pattern.	cope
Aggregate Velocity	Velocity is a property of a product backlog and not of a team; Therefore: have all Scrum teams for a single product backlog estimate together using a common baseline and range	2014/4/18. Done	Needs sketch. No new workshop	cope
Pigs Estimate	Estimates should be grounded in reality rather than wishful thinking; Therefore: Let those who are going to do the work do the estimation		Needs sketch. No new workshop	gb
Specialized Velocities	It's hard to do Aggregate Velocity if you have too many teams; Therefore: Specialize teams (not individuals) and let each one estimate and build PBIs matched to their specialization	2014/4/18. Done	Needs sketch and cleanup from workshop. No additional workshop.	cope
ROI	You need to order the items in the backlog; Therefore: order them such that you achieve the highest long-term ROI if delivered in the order of the Product Backlog	4/21/2014	Needs Sketch. No additional workshop.	cope
Yesterday's Weather	People tend to set increasingly high goals for themselves to the point of not being able to achieve them; Therefore: Use the previous Sprint's velocity as the best indicator of the next Sprint's velocity	2014/4/16. Done.	Needs sketch. No new workshop	cope
Product Backlog Items	You want to organize work to optimize ROI; Therefore: Create PBIs to describe concrete product increments that increase value for stakeholders	2014/4/18. Done	Needs sketch. No new workshop	cope
Product Owner	You need a single, ordered product backlog. Therefore: Get a Product Owner with deep business experience and domain knowledge to create the backlog.	2014/4/17. Great pic. See it.	Needs Sketch. No new workshop.	cope
Surrogate Product Owner	If the product being developed does not have a Product Owner, then the responsibility rolls all the way back to the team		Needs Sketch. No new workshop.	jeos
Teams that finish early tend to accelerate faster	If you fail too many Sprints it's discouraging: failure comes from taking too many points into the Sprint. Therefore: use Yesterday's Weather to get about the right number of points; use Scrumming the Scrum to lubricate the acceleration; and realize the acceleration by taking on more work if you do finish early.		Needs to be put into Alexandrian form. Needs sketch. No new workshop.	js
Surrogate Product Owner	If the product being developed does not have a Product Owner, then the responsibility rolls all the way back to the team		Workshopped at ScrumPLoP 2010. Awaiting revision into Alexandrian form. Needs sketch.	jeos
Spirit of the Game	Rules create loopholes. Therefore: Use the rules as a guide, but be driven by The Spirit Of the Game in cases where the rules' applicability is ambiguos or contentious.		Workshopped at ScrumPLoP 2013. Awaiting revision	lh / jeos
Beyond the Happy Bubble	Teams become victims of groupthink; Therefore: Have a catalyst who actively keeps the team a bit uncomfortable		Needs to be put into Alexandrian form. No new workshop.	nbh
Swarming: One-Piece Continuous Flow	Handoffs lead to poor feedback loops; Therefore: Have the team all work together on one item at a time		Needs to be put into Alexandrian form. No new workshop.	js
Illegitimus Non Interruptus	There are always emergent requirements, and Scrum accommodates these in its velocity, yet some need business attention. Therefore: give the Product Owner discretion over some fraction of the team's velocity to accommodate market changes.		Needs to be put into Alexandrian form. No new workshop.	js
Sprint Planning Meeting	There is a discontinuity between "what" and "how" in the Value Stream; therefore: create a ceremony to manage that transition		Needs Sketch. No additional workshop.	???
Sprint Retrospective	Entropy erodes organizations. Over time, without explicit attention, processes and discipline tend to decay. People get sloppy. Therefore: At the end of each Sprint, before the next one, hold a meeting for self-examination of the team’s behavior during the previous Sprint.		Done	nbh & mb
Small Changes	Product Owner is a big job—too big for multiple teams. Therefore: Organize the Product Owner role into a Lead Product Owner and Co-Product Owners.		Duplicates Product Owner Team	el
Product Backlog			Done	cope
Vision			Done	lh
SheepDog	ScrumMaster pattern		Done	nbh
Remove the Shade	A team's overall effectiveness can be limited by individuals' prowess or overzealousness. Therefore: Increase overall team effectiveness by removing people who become overly central to the team's functioning.		Done	gb & df
Beyond the Happy Bubble	Teams become victims of groupthink; Therefore: Have a catalyst who actively keeps the team a bit uncomfortable		Done	gpb, nbh
Developer-Ordered Work Plan	The Product Owner has no say on how the team should do its work, yet the team should have an attitude of commitment towards delivery. Therefore: Do not allow any extrinsic ordering of the Development Team's work program, but let them self-organize.		Done	cope
Limited Duration Projects	You can't release every Sprint, so limit the amount of time for a project.		Afbryded	dg
Team Sprint	Done		Done	vpe
Release Range	Done		Done	vpe
Release Plan	Done		Done	vpe
Illigitimus Non Interruptus	Done		Done	js
Scrumming the Scrum	Done		Done	js
Knight of the Mirrors	ScrumMaster pattern		Done	nbh
Daily Clean Code	Done		Done	js, nbh
DoneMaster	ScrumMaster pattern		Done	nbh
Catalyst	Scrum Master pattern		Done	nbh
Coach	ScrumMaster pattern		Done	nbh
Cross-Functional Teams			Done	gb & lh
Teams that finish early tend to accelerate faster			Done	js
Scrum Emergency Procedure			Done	js
Give Managers Work / Involve the Managers			Done	gpb, nbh
Stable Teams	Teams can't get velocity unless they build mutual trust and familiarity. Therefore: keep teams relatively stable over time.		Done	gb & lh
Sprint Backlog			Done	nbh, mb
Sprint			Done	cope
Oyatsu Jinja			Done	kh
Kaizen Pulse			Done	cope
Vacation PBI			Done	cope
Norms of Conduct			Done	Cesário
Optimization Teams	As the number of teams using Scrum grows they will face impediments and create valuable knowledge on solving them in their specific setting. Therefore: Form optimization teams consisting of people from the various Scrum Teams to capture the created knowledge so that the teams and organization can learn from it.		Done	Cesário
Sprint Planning Meeting			Done	cope
Happiness Metric			Done	js
Sprint Goal			Done	nbh / js